Software Project Management Plan

SPMP

Vacanza

Team 2

Ahmet Serhat Şahin, 22101813

Damla Alçay, 22002369

Göksu Uzun, 22102745

Ömer Faruk Asil, 22002781

Ufuk Zencirci, 22102476

Bilkent University

Department of Information Systems and Technologies

27.12.2025

- Change History

| File Name | Document Type | Deliverable | Version | Submission Date |
| --- | --- | --- | --- | --- |
| Team2_SPMP_V1 | Microsoft Word 2024 Document (.docx) | 3 | 1 | 7.12.2025 |
| Team2_SPMP_V2 | Microsoft Word 2024 Document (.docx) | 3 | 2 | 27.12.2025 |

- Change List

- Entire document - References are added for the Functional Requirements  used, from previous documents (SRS).

- Section 1.1 - Added documentation-related work packages (WP0.x).

- Section 1.1 - Inserted a summary paragraph before the Work Packages table and added reference to the SRS.

- Section 2.1 – WBS Decomposition-Based Estimation: The missing explanatory text was added to clarify the WBS-based effort estimation approach. The unit of estimated effort was explicitly specified as person-hours, and the previously missing documentation-related effort was incorporated into this section.

- Section 2.2 – Use Case-Based Estimation: The missing explanatory text was added, and the omitted use case was included. Additionally, all effort units previously expressed as man-hours were revised to person-hours to ensure consistency and correctness.

- Section 2.3 – Agile Estimation: The missing explanatory text was added to describe the Agile-based estimation approach. The method used for assigning story points was clearly explained, and the reference relationships between user stories and the Functional Requirements defined in the SRS were reviewed and updated to ensure proper traceability.

- Executive Summary: The Executive Summary is revised into a single-paragraph, one-page text that explicitly states numeric effort estimates (in person-hours) and the total project cost, as required by the feedback.

- Section 3 -Project Monitoring and Measuring is streamlined by removing metrics that will not be reliably collected and keeping only practical, tool-supported measurements that can be tracked consistently.

- Section 4 - Software Development Environment is updated with brief explanatory text that defines the purpose of the toolchain and references the table as the baseline development environment.

- Project Details

| Project Name | Vacanza - AI Powered Travel Application |
| --- | --- |
| Software Product Name | Vacanza |
| Company Name | No sponsor company |
| Academic Advisor | Neşe Şahin Özçelik |
| Github URL | https://github.com/VacanzaTravelApp |
| WEB page | https://vacanza.app |
| Software Product Information | Vacanza is an AI-powered travel assistant that helps users plan their trips in a smart, personalized, and effortless way. The application uses artificial intelligence to design customized travel routes based on each user’s interests, preferences, and travel style—whether they enjoy culture, food, history, or nature. Vacanza combines everything a traveler needs in one place: cultural and event recommendations, interactive 2D/3D maps, booking connections for flights and accommodation, and calendar synchronization for easy scheduling. Thanks to its AI system, Vacanza can also adapt plans dynamically according to weather, time, or local events, and provide instant suggestions through a friendly chatbot. In short, Vacanza turns travel planning into a smooth, intelligent, and enjoyable experience by offering a truly personalized journey for every user. |

- Team 2

| Name, Surname | Bilkent e-mail | Alternative e-mail |
| --- | --- | --- |
| Ahmet Serhat Şahin | serhat.sahin@ug.bilkent.edu.tr | aserhatsahin@gmail.com |
| Damla Alçay | damla.alcay@ug.bilkent.edu.tr | alcaydamla2@gmail.com |
| Göksu Uzun | goksu.uzun@ug.bilkent.edu.tr | goksuzun@gmail.com |
| Ömer Faruk Asil | faruk.asil@ug.bilkent.edu.tr | asilo02@hotmail.com |
| Ufuk Zencirci | ufuk.zencirci@ug.bilkent.edu.tr | ufuq.zencirci@gmail.com |

- Individual Contributions Overview

| Name, Surname | Summary of Contributions to the SRS Document |
| --- | --- |
| Ahmet Serhat Şahin | Executive Summary Project Monitoring Software Development Environment Project Effort Estimation |
| Damla Alçay | Project Effort Estimation |
| Göksu Uzun | Project Schedule General Formatting Discussions |
| Ömer Faruk Asil | Project Effort Estimation |
| Ufuk Zencirci | Project Schedule Discussions |

### Executive Summary

This Software Project Management Plan (SPMP) for Vacanza documents how Team 2 will plan, execute, monitor, and control the project over the course timeline, covering scope and assumptions, roles and responsibilities, the Work Breakdown Structure (including documentation-related work packages), milestone-based scheduling across increments, effort and cost estimation, risk/issue handling, and the software development environment/toolchain used to deliver and verify the product. In this SPMP we decomposed the project into manageable work packages, mapped them to a realistic schedule and ownership, and produced an estimation baseline using three complementary techniques: WBS-based estimation, Use Case Points (UCP), and Agile story points (with a documented rule for how story points are assigned and how they map to sprint planning). All effort values are reported in person-hours and compared across methods; the results show that WBS and UCP converge at roughly ~3.1k person-hours, while the Agile estimate is lower at roughly ~1.88k person-hours because it primarily reflects functional user stories whereas WBS/UCP also include overhead such as integration, infrastructure, testing, coordination, and documentation—therefore the SPMP adopts the WBS estimate as the primary effort baseline (validated by UCP) and reserves story points for iteration-level tracking and velocity. We also established a cost baseline by listing resources and direct expenses and summarizing the total estimated out-of-pocket cost as 19,920 TL + 360 USD, supported by monthly cash-flow and NPV calculations to make the financial impact explicit. Finally, the plan defines how project and product progress will be measured (which metrics will be collected, where they will be stored, and how they will be evaluated using tools like Jira/GitHub) and documents the complete development environment (languages, frameworks, databases, APIs, cloud/CI/CD, testing and collaboration tools) to ensure a consistent and traceable delivery process.

### Table of Contents

Page Number

Executive Summary	v

Table of Contents	vi

1.	Project Schedule	10

1.1.	Work Packages & Dependencies	10

1.1.1. Milestone-1 (this semester): - 1st Increment (20% of the functionality)	12

1.1.2. Milestone-2 (next semester): - 2nd Increment (Additional 40% of the functionality)	13

1.1.3. Milestone-3 (next semester) – Final Increment (Additional 40% of the functionality)	14

1.2.	Resource Requirements	15

1.3.	Cost Estimation, Net Present Value, Budget and Resource Allocation	19

2.	Project Effort Estimation	23

2.1.	WBS Decomposition-Based Estimation	23

2.2.	Use Case Based Estimation	24

2.3.	Agile Estimation	28

2.4.	Discussion	30

3.	Project Monitoring and Measuring	32

3.1.	Monitoring Approach	32

3.2.	Project Metrics	33

3.3.	Product Metrics	33

3.4.	Process Metrics	34

3.5.	Data Storage and Usage of Metrics	34

4.	Software Development Environment	36

5.	Discussions	39

List of Tables

Page Number

Table 1 Work Packages and Dependencies	10

Table 2 Project Expenditures	19

Table 3 WBS Effort Estimation	23

Table 4 Unadjusted Actor UCP	25

Table 5 Unadjusted Use Cases UCP	26

Table 6 Technical Factor Table	26

Table 7 Environmental Factor Table	27

Table 8 User Stories	28

Table 9 Software Development Environments	36

List of Figures

Page Number

Figure 1 Cash Flow Diagram for Vacanza	20

Figure 2 Use Case Diagram for Vacanza (Representing First Increment)	25

Abbreviations

| CTIS E EF FReq NPV SP | Information Systems and Technologies Expenditure Environmental Factor Functional Requirements Net Present Value Story Point |
| --- | --- |
| SPMP | Software Project Management Plan |
| SRS T UC UCP US WBS | Software Requirements Specification Technical Factor Use Case Use Case Points User Story Work Breakdown Structure |
| WP | Work Package |

# Project Schedule

## Work Packages & Dependencies

WBS presented in Table 1 was developed by systematically decomposing the project scope and deriving actionable work packages from the Functional Requirements (FReq) and Use Cases defined in the SRS. The schedule follows a logical execution flow that begins with project management and documentation activities (WP0.x), ensuring that planning artifacts including the Initial Plan, SRS, SPMP, and SDD are completed before and alongside technical development. Subsequent work packages transition into infrastructure setup and feature implementation, where the “Predecessor” column enforces critical dependencies for example, ensuring that the infrastructure layer (WP1) is fully established before feature implementation (WP2) begins.

Table 1 Work Packages and Dependencies

| Work Package ID | Work Package Name | Predecessor Work Package IDs | Team Member(s) Assigned |
| --- | --- | --- | --- |
| WP0.1 | Initial Plan Preparation | - | ALL Team |
| WP0.2 | SRS Preparation & Revision | WP0.1 | ALL Team |
| WP0.3 | SPMP Preparation & Revision | WP0.2 | ALL Team |
| WP0.4 | SDD Preparation | WP0.3 | ALL Team |
| WP1.1.1 | Configure DigitalOcean Droplet & Network Security | - | Ömer Faruk Asil |
| WP1.1.2 | Setup Docker Environment & Container Config | WP1.1.1 | Ömer Faruk Asil |
| WP1.1.3 | Initialize PostgreSQL Database Schema & Migration | WP1.1.2 | Ömer Faruk Asil |
| WP1.1.4 | Configure Firebase Project & Service Accounts | - | Göksu Uzun |
| WP2.1.1 | Create Backend Security Filter (Firebase JWT) | WP1.1.4 | Ufuk Zencirci Göksu Uzun |
| WP2.1.2 | Create API for User Registration (DB Insert) | WP2.1.1 | Göksu Uzun Ufuk Zencirci |
| WP2.1.3 | Create API for User Login & Profile Fetch | WP2.1.1 | Ufuk Zencirci Ömer Faruk Asil Göksu Uzun |
| WP2.2.1 | Implement Mobile Login/Register UI Screens | - | Ahmet Serhat Şahin |
| WP2.2.2 | Implement Web Login/Register UI Components | - | Damla Alçay |
| WP2.3.1 | Integrate Mobile Auth with Backend APIs | WP2.1.2, WP2.2.1 | Ahmet Serhat Şahin |
| WP2.3.2 | Integrate Web Auth with Backend APIs | WP2.1.2, WP2.2.2 | Damla Alçay |
| WP3.1.1 | Integrate Mapbox SDK into Backend (GeoJSON) | WP1.1.3 | Göksu Uzun Ufuk Zencirci Ömer Faruk Asil |
| WP3.1.2 | Create APIs for Saving/Retrieving Custom Areas | WP3.1.1 | Göksu Uzun Ufuk Zencirci Ömer Faruk Asil |
| WP3.2.1 | Implement Mobile Map View & Touch Gestures | - | Ahmet Serhat Şahin |
| WP3.2.2 | Implement Web Map View & Drawing Tools | - | Damla Alçay |
| WP3.3.1 | Connect Mobile Map to Backend Geo-Data | WP3.1.2, WP3.2.1 | Ahmet Serhat Şahin |
| WP3.3.2 | Connect Web Map to Backend Geo-Data | WP3.1.2, WP3.3.2 | Damla Alçay |
| WP4.1.1 | Setup Amadeus API Credentials & Client | WP1.1.1 | Ömer Faruk Asil |
| WP4.1.2 | Create Backend Service for Flight Search | WP4.1.1 | Ufuk Zencirci |
| WP4.1.3 | Create Backend Service for Hotel Search | WP4.1.1 | Göksu Uzun |
| WP4.2.1 | Create Web Booking Search & Results UI | - | Damla Alçay |
| WP4.2.2 | Create Mobile Booking Search & Results UI | - | Ömer Faruk Asil |
| WP4.3.1 | Validate Booking Data Flow (End-to-End) | WP4.1.2, WP4.2.1 | Göksu Uzun Ufuk Zencirci |
| WP5.1.1 | Setup Python Microservice Environment | WP1.1.2 | Ömer Faruk Asil |
| WP5.1.2 | Develop Recommendation Algorithm Logic | WP5.1.1 | ALL Team |
| WP5.1.3 | Create Internal API for Spring-Python Communication | WP5.1.2 | ALL Team |
| WP5.2.1 | Implement Chatbot UI (Web) | - | Damla ALçay |
| WP5.2.2 | Implement Chatbot UI (Mobile) | - | Ahmet Serhat Şahin |
| WP6.1.1 | Implement AR Camera Overlay Logic (Mobile) | - | Ahmet Serhat Şahin |
| WP6.1.2 | Implement Micro-Location Geofencing Logic | - | Ahmet Serhat Şahin |
| WP6.1.3 | Create Backend API for Geofence Verification | WP3.1.1 | Göksu Uzun Ufuk Zencirci |
| WP6.1.4 | Integrate Mobile AR/Check-in with Backend | WP6.1.2, WP6.1.3 | Ahmet Serhat Şahin |
| WP7.1.1 | Design Gamification Logic (XP/Badges) in DB | WP1.1.3 | Göksu Uzun Ufuk Zencirci Ömer Faruk Asil |
| WP7.1.2 | Create APIs for Updating User XP/Progress | WP7.1.1 | Göksu Uzun Ufuk Zencirci Ömer Faruk Asil |
| WP7.2.1 | Implement Mobile Gamification UI (Profile/Badges) | - | Ahmet Serhat Şahin |
| WP7.2.2 | Implement Web Gamification UI (Profile/Badges) | - | Damla Alçay |
| WP7.3.1 | Connect Gamification UI to Backend | WP7.1.2, WP7.2.1, WP7.2.2 | Göksu Uzun Ufuk Zencirci Ömer Faruk Asil |
| WP8.1.1 | Create Analytics & Logs APIs (Backend) | WP1.1.3 | Ömer Faruk Asil |
| WP8.1.2 | Create Admin Dashboard Layout (Web Only) | - | Damla Alçay |
| WP8.1.3 | Implement Real-Time Charts & Data Tables | WP8.1.1 | Damla Alçay |
| WP8.1.4 | Integrate Admin UI with Analytics APIs | WP8.1.3 | Damla Alçay |
| WP9.1.1 | Create Test Suites for Increment 1 (Auth/Map) | WP2.3.1, WP3.3.1 | Damla Alçay |
| WP9.1.2 | Execute Integration Tests for Booking APIs | WP4.3.1 | Ömer Faruk Asil |
| WP9.1.3 | Verify Mobile AR Features (Increment 3) | WP6.1.4 | Ahmet Serhat Şahin |
| WP9.1.4 | Final System Acceptance Testing | All WPs | ALL Team |

Milestone-1 (this semester): - 1st Increment (20% of the functionality)

Objective & Scope: The primary goal of the first increment is to establish a stable cloud infrastructure and deliver the "Minimum Viable Product" (MVP) core features. This phase focuses on securing user access, enabling the primary geospatial interface, and demonstrating the system's ability to connect with external travel providers. In parallel with the technical work, this milestone also includes project management and documentation activities to prepare and revise the Initial Plan, SRS, and SPMP, ensuring alignment between planned scope, implementation, and academic deliverables.

Implemented Use Cases: The following Use Cases will be functional by the end of this milestone:

UC1.1: Create Account / Login (User Authentication).

UC1.2: Custom Area Selection & POI Integration.

UC1.3: View Map Layers.

Task Allocation & Responsibilities:

- Infrastructure & Database (WP 1.0):

  - Göksu Uzun & Ömer Faruk Asil: Configuration of DigitalOcean droplets, Docker containerization, and PostgreSQL database initialization.

- User Management (WP 2.0):

  - Ufuk Zencirci: Implementation of backend JWT/Firebase verification logic.

  - Ahmet Serhat Şahin & Damla Alçay: Development of Login/Register screens for Mobile and Web platforms respectively.

- Map Services (WP 3.0):

  - Göksu Uzun & Ufuk Zencirci & Ömer Faruk Asil: Backend logic for Mapbox API integration and geometric queries.

  - Ahmet Serhat Şahin: Mobile map rendering and custom drawing tools.

  - Damla Alçay: Web-based interactive map integration and layer filtering components.

Milestone-2 (next semester): - 2nd Increment (Additional 40% of the functionality)

Implemented Use Cases: The following Use Cases will be functional by the end of this milestone:

UC1.4: Generate Personalized Routes (AI Engine).

UC1.5: Adjust Itinerary.

UC1.8: Booking Integration.

UC1.6: Chat with AI Assistant.

UC1.10: Synchronize Calendar.

UC1.12: View Local Prices & Convert Currencies.

Task Allocation & Responsibilities:

- AI Engine & Chatbot (WP 5.0):

  - All Team Members: Development of the Python microservice integration, route logic, and recommendation algorithms.

  - Ahmet Serhat Şahin: Mobile Chat UI and route visualization.

  - Damla Alçay: Web Chat UI and itinerary display.

- Travel Services (WP 5.0 - Continued):

  - Ömer Faruk Asil, Ufuk Zencirci & Göksu Uzun: Development of the Python microservice integration, route logic, and recommendation algorithms.

  - Ahmet Serhat Şahin: Mobile implementation for calendar sync permissions and currency display.

  - Damla Alçay: Web implementation for exporting itineraries to calendar and toggling currencies.

Milestone-3 (next semester) – Final Increment (Additional 40% of the functionality)

Objective & Scope: The final increment addresses advanced mobile-specific features, user engagement (Gamification), and administrative oversight. This phase concludes with full system integration and comprehensive testing to ensure a polished final product.

Implemented Use Cases: The following Use Cases will be functional by the end of this milestone:

UC1.7: Location Based Check-in.

UC1.11: Explore in AR Mode.

UC1.9: Earn Badges & XP (Gamification).

UC2.1 & UC2.2: Administrative Monitoring & Analytics.

Task Allocation & Responsibilities:

- Advanced Mobile Features (WP 6.0):

  - Ahmet Serhat Şahin: Implementation of AR overlays using camera sensors and GPS-based check-in logic.

  - Göksu Uzun, Ömer Faruk Asil & Ufuk Zencirci: Backend support for geospatial verification.

- Gamification (WP 7.0):

  - Göksu Uzun, Ömer Faruk Asil & Ufuk Zencirci: Backend logic for tracking XP and triggering badge awards.

  - Ahmet Serhat Şahin: Mobile gamification UI.

  - Damla Alçay: Web profile and badge display.

- Admin Dashboard (WP 8.0):

  - Damla Alçay: Development of the web-based administrative panel for system monitoring.

  - Ömer Faruk Asil, Göksu Uzun & Ufuk Zencirci: Backend endpoints for system metrics.

- System Integration (WP 9.0):

All Team: Execution of final integration tests and bug fixing across all modules.

## Resource Requirements

This subsection provides, as a function of time, the resources required to complete the Vacanza project over two semesters (Fall 2025 and Spring 2026). The required resources include personnel, computer hardware, software and support tools, office facilities, travel, and maintenance activities. For each resource category, we explain how the need evolves between the documentation-oriented first semester and the implementation-focused second semester, and we relate these requirements to the cost items defined in the previous “Cost Estimation, Net Present Value, Budget and Resource Allocation” subsection.

Personnel Resources

The Vacanza team consists of five CTIS students who form the core development team. Roles (Product Owner, Scrum Master, web frontend developer, mobile developer, backend developer, AI and integration support) are stable across both semesters, but the weekly effort increases over time:

- Fall 2025 (September–December)

Each team member allocates approximately 8–10 hours per week. The focus is on requirements analysis, architectural and UI design, and project documentation (Initial Plan, SRS, SPMP, and preparation for SDD), as well as the first increment prototype.

- Spring 2026 (January–May)

Each team member allocates approximately 12–15 hours per week. The focus shifts to implementation of the web and mobile applications, backend and API integration, AI and map features, system testing, and preparation of the final deliverables (final prototype and poster).

Personnel time is not budgeted as salary, because all team members are students working within the scope of the senior project course. The economic impact of their effort is reflected indirectly through other cost items such as home-office utilities, transportation, meeting expenses, and AI subscriptions, rather than hourly labor rates.

Computer Hardware Resources

- All development and documentation activities are performed on personal computers:

- Each team member uses a personal laptop capable of running:

  - VS Code or IntelliJ IDEA for coding

  - Docker for containerized services

  - Postman for requests

  - Web browsers and Flutter tooling for UI development and testing

- No separate mobile test devices or campus lab machines are dedicated to the project. Occasional checks on personal smartphones are performed (e.g., viewing the web UI on a phone browser), but no additional hardware is purchased specifically for Vacanza.

Because all devices are pre-owned, there is no direct hardware acquisition cost for the project. The implicit cost of using personal laptops and home hardware (electricity, internet, and wear-and-tear) is captured under the home office utilities and equipment usage item in the cost estimation section (E3, 5,400 TL).

Software and Support Tools

The Vacanza project uses a consistent set of development, collaboration, and documentation tools throughout both semesters. The intensity of their use increases in Spring 2026 as the project moves into full-scale development and testing.

- Development tools

  - VS Code: used by the web and mobile developers for React and Flutter development.

  - IntelliJ IDEA: used by backend developers for Spring Boot and Java, under student licensing.

  - Docker: used to run and orchestrate backend services and databases in containers, in free edition.

  - Postman: used to design and test endpoints.

- Version control and project management

  - GitHub and GitHub Desktop: used for source code management, branching, pull requests, and code reviews.

  - Jira: used for issue and task tracking, sprint planning, and backlog management.

  - Mattermost: used for real-time notifications about commits, pull requests, and task updates. Additionally, general communications about Vacanza and its documents.

- Design and documentation

  - Figma: used for UI/UX design and screen prototypes.

  - Google Docs: used for collaborative editing of all major documents (Initial Plan, SRS, SPMP, SDD).

  - WhatsApp: used as an additional communication channel for quick coordination within the team and with the advisor.

- AI tools

  - ChatGPT Pro: used continuously from September 2025 to May 2026 for documentation support, architecture and design discussions, code explanations, and general research assistance. The team uses four Pro accounts shared among five members. Since these subscriptions are also used for other courses and personal purposes, approximately 50% of the total subscription cost is allocated to Vacanza and reflected as a project cost (E5, 360 USD).

  - Google Gemini Advanced (student offer): used in parallel with ChatGPT for research, text generation, and idea exploration. Gemini is obtained through a one-year free student offer, so it does not generate any direct monetary cost for the project. Its contribution is therefore considered a productivity gain rather than a cost item.

- Cloud services and APIs

  - Application stack components such as React, Flutter, Spring Boot, PostgreSQL, Firebase, Mapbox, and hosting through the GitHub Student Developer Pack are used under free or student tiers. While a Mapbox API or a DigitalOcean droplet would normally incur charges beyond certain limits, the team expects to remain within free thresholds for the duration of the project and to use additional student quotas, hopefully, if necessary.

With the exception of ChatGPT Pro, all listed software and support tools are treated as zero direct cost to the project because they are available either as free tools or under educational programs. Their primary resource impact is in terms of configuration and maintenance time, rather than monetary expenditure.

Office Facilities and Working Environment

The team does not rely on dedicated university laboratories for day-to-day work. Instead, activities are carried out in:

- Home working environments, where each member uses their personal laptop, internet connection, and workspace to implement features, write documentation, and conduct online meetings.

- Occasional meetings in informal environments (e.g., cafes or common areas) for sprint discussions, design reviews, and advisor feedback.

The cost associated with the home working environment (electricity, internet, heating/cooling, and general equipment usage) is included in E3 (home office utilities and equipment usage). University facilities are available as part of the academic program and therefore do not create additional direct costs.

Travel and Meeting Resources

Face-to-face meetings are planned mainly for the second semester, with some starting in late Fall 2025:

- Beginning from Jan 2026 and continuing until May 2026, the team plans approximately two in-person Vacanza meetings per month (12 meetings in total).

- These meetings are typically held in or around campus. Four members travel by car, and one member lives on campus.

The required resources include:

- Travel: cars, fuel, and occasional parking.

- Meeting spaces: cafes or similar venues where the team can work and discuss the project.

The monetary impact is explicitly represented in the cost estimation section:

- (8,400 TL): beverages and café costs across all planned Vacanza meetings.

- E2 (4,800 TL): transportation costs for members who use cars to attend the meetings.

- E6 (720 TL): a one-time face-to-face meeting of the Vacanza Startup Studio sub-team, covering both beverages and transportation.

These items form the primary travel and meeting-related resource requirements of the project.

Maintenance and Support Requirements

Maintenance and support activities span both semesters and primarily require team time rather than new tools:

- Regularly updating development tools (VS Code, IntelliJ, Docker, Postman) and libraries.

- Managing GitHub repositories, enforcing branch policies, and keeping the codebase consistent with Jira tasks.

- Monitoring usage of free tiers for Mapbox, Firebase, hosting, and other external services to avoid unexpected charges.

- Maintaining alignment between documentation (Initial Plan, SRS, SPMP, SDD) and the evolving implementation.

These maintenance activities are part of the normal workload assigned to team members and do not introduce additional direct costs beyond those already accounted for under home office utilities, AI subscriptions, and travel and meeting expenditures.

Consumables and Small Items

- Coffee, tea and other beverages during meetings

- Snacks and meals (some brought from home, some bought outside)

- Notebooks, pens (for those who prefer handwriting)

- Digital note-taking on laptops, tablets or phones (no extra cost beyond hardware)

- One printed project poster for the final presentation

## Cost Estimation, Net Present Value, Budget and Resource Allocation

- Cost Estimation

This subsection summarizes how the Vacanza team allocates its limited student budget and non-monetary resources across the two-semester project. The team does not receive any salary or dedicated funding; therefore, all costs correspond to out-of-pocket expenses (coffee, transportation, printing, subscriptions) and the implicit cost of using personal equipment and home infrastructure (laptops, electricity, internet).

The table below lists the main expenditure items identified for the project. The amounts include both realized costs in Fall 2025 (September–December) and expected costs for Spring 2026 (January–May). TL costs mainly come from future face-to-face meetings, transportation, and utilities, while USD costs correspond to AI tool subscriptions.

These expenditure items are directly linked to key project functions and activities such as requirements and design meetings, development work performed at home, documentation and prototyping supported by AI tools, and final presentation and dissemination of the project results.

Table 2 Project Expenditures

| Expenditure ID | Explanation | Cost (in TL or USD) |
| --- | --- | --- |
| E1 | Planned face-to-face Vacanza team meetings for the next 6 months. The team expects 2 meetings per month, with 5 people attending and everyone buying one drink (≈140 TL per drink). | 8,400 TL |
| E2 | Transportation for these face-to-face meetings. For each meeting, 4 members travel by car (1 member lives on campus). Estimated cost is nearly 100 TL per car per meeting (fuel + distance varieties). | 4,800 TL |
| E3 | Home office utilities and equipment usage: allocated portion of electricity, heating/cooling, and home internet bills plus the wear-and-tear cost of personal laptops and peripherals used for Vacanza development between September 2025 and May 2026. | 5,400 TL |
| E4 | Final project poster printing near the end of the second semester. | ≈ 600 TL |
| E5 | ChatGPT Pro subscriptions used by the team for Vacanza documentation, design, and development. There are 4 Pro accounts shared among 5 members, each costing about 20 USD per month. The subscriptions are also used for other courses and personal work, so only 50% of the total subscription cost is allocated to Vacanza. Assumption: subscriptions are active from September 2025 to May 2026. | 360 USD |
| E6 | One face-to-face meeting for the Vacanza Startup Studio sub-team (4 people), including 3 coffees and car transportation for 3 members. | 720 TL |

Total estimated TL expenditures: 19,920 TL

Total estimated USD expenditures: 360 USD

The cash flow below covers the full project timeline from September 2025 to May 2026, which are both semesters. Additionally, when constructing the cash flow diagram, we follow the End-of-Month approach: all expenses that occur within the same month are aggregated and shown as a single cash outflow at the last day of that month.

Figure 1 Cash Flow Diagram for Vacanza

- Net Present Value (NPV) Calculation

To reflect the time value of money, each monthly cash outflow in the cash flow table is discounted back to 1 September 2025 (Point 0) using the given monthly interest rates:

Monthly interest rate for TL cash flows: 3% (0.03)

Monthly interest rate for USD cash flows: 0.1% (0.001)

For a cash outflow ( CFₜ ) that occurs at the end of month ( t ), the present value (PV) is computed as:

PVₜ = CFₜ / (1 + r)ᵗ

where ( r = 0.03 ) for TL-denominated costs and ( r = 0.001 ) for USD-denominated costs.

Example for TL (December 2025):

TL cash outflow at the end of December (month index ( t = 4 )): 2,800 TL.

PV_Dec_TL = 2,800 / (1 + 0.03)⁴ ≈ 2,487.76 TL

Example for USD (February 2026):

Vacanza-allocated ChatGPT Pro cost at the end of February (month index ( t = 6 )): 40 USD.

PV_Feb_USD = 40 / (1 + 0.001)⁶ ≈ 39.76 USD

Applying the same formula to all months in the cash flow table and summing the discounted values yields:

Total NPV of TL cash flows:

NPV_TL = PV_Sept_TL + PV_Oct_TL + … + PV_May_TL ≈ 16,697 TL

Total NPV of USD cash flows (Vacanza share of ChatGPT Pro):

NPV_USD = PV_Sept_USD + PV_Oct_USD + … + PV_May_USD ≈ 358 USD

If we convert the USD part into TL using an illustrative exchange rate of 1 USD ≈ 35 TL, the combined present value of all expenditures becomes:

NPV_Total ≈ 16,697 TL + 358 × 35 TL ≈ 29,200 TL

This value represents the estimated economic cost of completing the Vacanza project, evaluated on 1 September 2025.

- Discussion

The NPV analysis shows that even for a student project with no salaries and no external funding, the cumulative cost is non-trivial. The largest portion of the budget is driven by small but recurring TL expenses, especially face-to-face meetings (coffee for each team member and transportation by car) and the continuous use of personal laptops and home infrastructure. What appears to be a minor cost per meeting or per month becomes significant when aggregated over two semesters.

The ChatGPT Pro subscriptions also appear as a visible cost item, even though only a fraction of the total subscription spending is allocated to Vacanza. These AI tools support many activities such as documentation, design decisions, and code reviews, and therefore contribute directly to productivity and quality. At the same time, the project explicitly accounts for the fact that these subscriptions are not used solely for Vacanza but also for other courses and personal tasks.

An important aspect of this project is that the team benefits heavily from the fact that we are students. Many potentially expensive tools and services (developer platforms, source control, collaboration tools, cloud services and APIs) are either free or heavily discounted under student programs and education licenses. For example, the Mapbox API normally starts charging beyond a certain threshold (such as more than 50,000 requests), but our expected usage for Vacanza is well below this limit, and even if we approached it we could still rely on additional free quotas available through individual student accounts. Similarly, a basic DigitalOcean droplet that would typically cost around 12 USD per month for hosting the backend and database is effectively free for us because we access it through the GitHub Student Developer Pack. In addition, the vacanza.app domain name is managed under an existing family-owned account, so the project does not pay any separate domain registration or renewal fees. For document formatting and polishing, the team occasionally uses a Microsoft 365 / Word license available through a family workplace account, which again does not introduce any extra license cost for the project. As a result, Vacanza does not currently incur any cost for items such as hosting infrastructure, external map and data APIs, the project domain name, or office software, even though these would represent significant budget items in a real startup or post-student setting.

Overall, the NPV of approximately 16,700 TL + 358 USD confirms that developing Vacanza requires a meaningful amount of resources, even in a university setting. This encourages the team to plan physical meetings carefully, to monitor the duration and intensity of paid subscriptions, and to continue leveraging student discounts and free tiers wherever possible in order to keep the total project cost under control.

# Project Effort Estimation

## WBS Decomposition-Based Estimation

In this subsection, the total project effort is estimated using a Work Breakdown Structure (WBS) decomposition approach. The main work packages (WP1–WP10) defined in Table 3 are organized according to the three project increments. For each work package, effort is estimated in person-hours by considering implementation workload, integration complexity, testing activities, coordination overhead, and the preparation of academic deliverables (IP, SRS, SPMP, and SDD). Effort values are determined through team discussion and validated for consistency with the assigned team size and planned durations.

Table 3 WBS Effort Estimation

| Work Package ID | Work Package Name | Estimated Effort | Assigned # of Team Members | Estimated Duration | Projected Start Date | Projected End Date |
| --- | --- | --- | --- | --- | --- | --- |
| WP0 | Documentation & Academic Deliverables (IP, SRS, SPMP, SDD) | 300 | 5 | 13 weeks | 01 Oct 2025 | 05 Jan 2026 |
| WP1 | Project Infrastructure & Database Setup (Cloud Environment, Docker, PostgreSQL, Firebase Config) | 220 | 2 | 3 weeks | 1 Oct 2025 | 31 Oct 2025 |
| WP2 | User Management & Authentication Module (Registration, Login APIs, Security Filters, Mobile/Web Login Screens) | 380 | 5 | 4weeks | 13 Nov 2025 | 15 Dec 2025 |
| WP3 | Map Services & Geospatial Core (Mapbox Integration APIs, Custom Area Selection Logic, Layer Filtering) | 420 | 5 | ~5 weeks | 20 Nov 2025 | 31 Dec 2025 |
| WP4 | Travel Services Integrations (Booking Redirects, Calendar Sync, Currency Conversion APIs) | 320 | 4 | 4 weeks | 01 Jan 2026 | 31 Jan 2026 |
| WP5 | AI Route Generation & Chatbot Engine (Route Logic, Chatbot API, Python Microservice Integration, Recommendation Algorithms) | 600 | 5 | 7 weeks | 01 Feb 2026 | 20 Mar 2026 |
| WP6 | Advanced Mobile Features (Augmented Reality (AR), Micro-Location Check-in) | 260 | 3 | 4 weeks | 1 Mar 2026 | 02 Apr 2026 |
| WP7 | Gamification System (Badges, User Achievements) | 220 | 5 | 3 weeks | 01 Apr 2026 | 28 Apr 2026 |
| WP8 | Administrative Dashboard (System Monitoring UI, Analytics Reports, User Logs APIs) | 260 | 2 | 4 weeks | 15 Feb 2026 | 20 Mar 2026 |
| WP9 | System Integration & Final Testing (Integration Testing, User Acceptance Testing, Bug Fixes) | 420 | 5 | 4 weeks | 1 Apr 2026 | 30 Apr 2026 |

WBS Estimated Effort (person-hours)  = 3400 Person/Hours

## Use Case Based Estimation

In this subsection, the project effort is estimated using the Use Case Point (UCP) method. The estimation is based on the latest version of the Use Case Diagram defined in the SRS document. The UCP approach evaluates the system size by considering the number and complexity of both actors and use cases, and refines the estimation through technical and environmental adjustment factors.

As an initial step, actors interacting with the Vacanza system are identified and classified as simple, average, or complex according to their interaction characteristics. Each actor category is assigned a predefined weight, and the resulting Unadjusted Actor Weight (UAW) is calculated, as summarized in Table 4. Subsequently, use cases are classified based on the number of transactions, leading to the computation of the Unadjusted Use Case Weight (UUCW) shown in Table 5. The final effort estimation is obtained by applying the Technical Complexity Factor (TCF) and Environmental Factor (EF), as presented in Tables 6 and 7.

Figure 2 Use Case Diagram for Vacanza (Representing First Increment)

Table 4 Unadjusted Actor UCP

| Actor Classification | Type of Actor | Weight | Number | Total |
| --- | --- | --- | --- | --- |
| Simple | External system that must interact with the system using a well-defined API | 1 | 0 | 0 |
| Average | External system that must interact with the system using standard communication protocols (e.g. TCP/IP, FTP, HTTP, database) | 2 | 6 | 12 |
| Complex | Human actor using a GUI application interface | 3 | 2 | 6 |
| Total Unadjusted Actor UCP |  |  |  | 18 |

Table 5 Unadjusted Use Cases UCP

| Use Case Classification | No. of Transactions | Weight | Number | Total |
| --- | --- | --- | --- | --- |
| Simple | 1 to 3 transactions | 5 | 3 (UC1.3, UC1.9, UC2.1) | 15 |
| Average | 4 to 7 transactions | 10 | 7 (UC1.1, UC1.5, UC1.6, UC1.7, UC1.10, UC1.12, UC2.2) | 70 |
| Complex | 8 or more transactions | 15 | 4 (UC1.2, UC1.4, UC1.8, UC1.11) | 60 |
| Total Unadjusted Use Case UCP |  |  |  | 145 |

Complex Actors: Traveler, Admin

Average Actors: Others

UUC = UAUCP + UUCP

UAW (Unadjusted Actor Weight) = 18
UUCW (Unadjusted Use Case Weight) = 145
UUCP = UAW + UUCW = 18 + 145 = 163

Table 6 Technical Factor Table

| Factor | Description | Weight | Assigned Value | Weight x Assigned Value |
| --- | --- | --- | --- | --- |
| T1 | Distributed system | 2.0 | 4 | 8.0 |
| T2 | Response time/performance objectives | 1.0 | 5 | 5.0 |
| T3 | End-user efficiency | 1.0 | 3 | 3.0 |
| T4 | Internal processing complexity | 1.0 | 4 | 4.0 |
| T5 | Code reusability | 1.0 | 3 | 3.0 |
| T6 | Easy to install | 0.5 | 5 | 2.5 |
| T7 | Easy to use | 0.5 | 5 | 2.5 |
| T8 | Portability to other platforms | 2.0 | 5 | 10 |
| T9 | System maintenance | 1.0 | 4 | 4.0 |
| T10 | Concurrent/parallel processing | 1.0 | 3 | 3.0 |
| T11 | Security features | 1.0 | 5 | 5.0 |
| T12 | Access for third parties | 1.0 | 5 | 5.0 |
| T13 | End user training | 1.0 | 1 | 1.0 |
| Total Technical Factors: |  |  |  | 56.0 |

TCF = 0.6 + (0.01 x T)

TCF = 0.6 + (0.01 x 56.0) = 1.16

Table 7 Environmental Factor Table

| Factor | Description | Weight | Assigned Value | Weight x Assigned Value |
| --- | --- | --- | --- | --- |
| EF1 | Familiarity with development process used | 1.5 | 4 | 6.0 |
| EF2 | Application experience | 0.5 | 3 | 1.5 |
| EF3 | Object-oriented experience of team | 1.0 | 4 | 4.0 |
| EF4 | Lead analyst capability | 0.5 | 4 | 2.0 |
| EF5 | Motivation of the team | 1.0 | 4 | 4.0 |
| EF6 | Stability of requirements | 2.0 | 3 | 6.0 |
| EF7 | Part-time staff | -1.0 | 2 | -2.0 |
| EF8 | Difficult programming language | -1.0 | 2 | -2.0 |
| Total Environmental Factor: |  |  |  | 19.5 |

EF = 1.4 + (-0.03 x E)

EF = 1.4 + (-0.03xx 19.5) = 1.4 - 0.585 = 0.815

UCP = UUC x TCF x EF

UCP = 163 x 1.16 x 0.815

UCP = 189.08 x 0.815 = 154.08

The final Use Case Point (UCP) for the Vacanza System is 154.08.

Converting  UCP to Effort (Person/Hours)

Effort (Hours) = UCP x H

H = 20 Hour/UCP

Effort(Hours) = 154.08 × 20 ≈ 3081.6 ≈ 3082 person-hours

The total estimated effort for the Vacanza System using the UCP method is ≈ 3082 Person/Hours

## Agile Estimation

Table 8 User Stories

| Functional Requirement ID (from SRS) | User Story ID | User Story description | Estimated SP |
| --- | --- | --- | --- |
| FReq1 | US1 | As a Traveler, I want to securely create an account and log in with email verification, so I can start planning my trip. | 5 |
| FReq2 | US2 | As a Traveler, I want the system to analyze my behavior, so the AI can provide me with highly personalized recommendations. | 8 |
| FReq3 | US3 | As a Traveler, I want the system to generate personalized AI route suggestions based on my preferences (budget, time), so I can find my ideal itinerary. | 13 |
| FReq4 | US4 | As a Traveler, I want to use real-time map overlay filters (e.g., restaurants, hotels,, 3D), so I can quickly customize the map view. | 3 |
| FReq5 | US5 | As a Traveler, I want the system to automatically adjust my itinerary based on unexpected events (e.g., closures reported by me), so my plan remains feasible. | 8 |
| FReq6 | US6 | As a Traveler, I want to integrate with third-party booking APIs for accommodation and transportation, so I can manage all bookings in one place. | 8 |
| FReq7 | US7 | As a Traveler, I want to synchronize my itinerary with my personal calendar, so I don't miss any planned events. | 5 |
| FReq8 | US8 | As a Traveler, I want to be rewarded with points and badges for visiting locations, so I am motivated to explore more. | 3 |
| FReq9 | US9 | As a Traveler, I want the system to automatically check me in based on my micro-location, so my progress is tracked for gamification. | 8 |
| FReq10 | US10 | As a Traveler, I want to explore nearby attractions using Augmented Reality (AR) mode, so I can have an immersive experience. | 13 |
| FReq11 | US11 | As a Traveler, I want to see live currency conversions and local cost forecasts, so I can effectively manage my budget. | 5 |
| FReq12 | US12 | As a Traveler, I want seamless, real-time synchronization of my data across all platforms (web/mobile), so I maintain data consistency. | 5 |
| FReq13 | US13 | As an Admin, I want an administrative dashboard to monitor system health and API status, so I can proactively manage the service. | 5 |
| FReq14 | US14 | As a Traveler, I want to manually select a custom area on the map and integrate POIs from that area into my route, so I can personalize my exploration. | 5 |

Total Story Points (SP) = 94

Story points were assigned using a relative estimation approach based on team consensus. The estimation was performed on user stories that were directly derived from the Functional Requirements (FReq1–FReq14) defined in the Software Requirements Specification (SRS) document. Each user story was evaluated by considering implementation complexity, technical uncertainty, integration effort (including AI services, AR components, external APIs, and multi-platform support), as well as testing requirements. A Fibonacci-based scale (3, 5, 8, and 13) was applied to ensure consistency across estimates.

Given the technical characteristics of the Vacanza system (such as AI-driven functionality, augmented reality features, multi-platform development, and extensive third-party API integrations) a higher-than-average conversion rate was selected. Accordingly, one story point (SP) was mapped to 20 person-hours.

Based on a total of 94 story points, the estimated development effort using the Agile approach is calculated as 1,880 person-hours. This estimation primarily reflects the implementation effort associated with the functional user stories (FReq1–FReq14). In contrast, the WBS-based and UCP-based estimations additionally account for activities such as infrastructure setup, system integration, final testing, documentation, and coordination overhead. Consequently, the Agile-based estimation is expected to yield a lower effort value while remaining consistent with the overall effort range derived from the other estimation techniques.

## Discussion

The three estimation techniques used in this project—WBS Decomposition, Use Case Points (UCP), and Agile Story Point Estimation—produce different total effort values, which is expected because each method is based on different assumptions and focuses on different aspects of the Vacanza system. In our case, the WBS-based estimation is approximately 3,100 man-hours, the UCP-based estimation is approximately 3,080–3,100 man-hours, and the Agile estimation is approximately 1,880 man-hours.

The UCP estimation is driven by the number and complexity of actors and use cases, adjusted with Technical and Environmental Factors. Since Vacanza includes AI-based route generation, AR features, multi-platform development, geospatial processing, and several external API integrations, the Technical Complexity Factor (TCF) and Environmental Factor (EF) increase the overall UCP value. After calibrating the “hours per UCP” parameter to 20 hours/UCP (based on the team’s capacity and WBS results), the UCP method yields a total effort that is very close to the WBS estimate. This shows that UCP provides a requirements-driven, slightly conservative estimate that validates the WBS result.

The Agile estimation starts from functional requirements converted into user stories and uses Story Points (SP) to express relative complexity. In our case, the backlog sums up to 94 SP, and we use a conversion rate of 20 man-hours per SP, resulting in approximately 1,880 man-hours. This value mainly reflects the implementation effort of functional user stories (FReq1–FReq14) defined in the Agile Estimation section. It does not fully account for infrastructure setup (WP1), system integration and final testing (WP9), documentation, meetings, learning curve, and other overhead. Therefore, it is expected that the Agile estimate is lowerthan the WBS and UCP values. Agile estimation is still very useful for sprint planning and tracking team velocity, but it naturally underestimates the full project effort in an academic environment.

The WBS-based estimation (≈3,100 man-hours) divides the project into concrete work packages such as infrastructure, authentication, map services, AI engine, AR module, gamification, dashboard, and system testing. Each WP has clearly defined responsibilities, predecessors, durations, and assigned team members. Because of this structure, the WBS method captures not only pure coding effort, but also integration, rework, deployment, and coordination activities. It sits in the same range as the UCP result, but is directly tied to our actual plan, milestones, and workload distribution.

In summary, the differences can be explained as follows:

- UCP emphasizes system complexity and uncertainty → produces a requirements-based, slightly conservative estimate close to 3,100 man-hours.

- Agile emphasizes team perception and velocity for functional stories → produces the lowest value (~1,880 man-hours) and does not fully include overhead and non-functional work.

- WBS emphasizes real work packages and implementation structure → produces a balanced estimate (~3,100 man-hours) that aligns with how the team will actually execute the project.

For the Vacanza system, the WBS-based estimation is considered the most realistic and accurate for overall project planning, while the UCP estimation supports and validates this value, and the Agile estimation is used mainly for fine-grained sprint planning and tracking.

# Project Monitoring and Measuring

This section explains how the Vacanza team will monitor and control the project to determine whether it is on schedule, ahead of schedule, or lagging behind. The monitoring approach is aligned with the Scrum-based development process and the milestones, work packages, and increments defined in the project plan.

## Monitoring Approach

Scrum Meeting Frequency

In the first semester, the team holds coordination meetings approximately every three days, focusing on documentation tasks and the first increment prototype. In the second semester, the frequency is increased to daily scrums during active development and integration phases. In each short meeting, team members briefly state what they have done since the previous meeting, what they will do next, and if they have any blockers. This helps detect delays or bottlenecks early.

Sprint Planning and Sprint Review Meetings

At the beginning of each sprint, the team plans tasks and assigns them to use cases and backlog items, based on the backlog and milestones. At the end of each sprint, a Sprint Review is held to demonstrate the completed functionality (e.g., map filtering and area selection in the first increment, AI route generation in the second increment, and advanced mobile features and admin dashboard in the final increment). Deviations between planned and completed scope are discussed and reflected in the next sprint plan.

Project Advisor Meetings (Zoom / Face-to-Face)

Regular meetings with the academic advisor are conducted via Zoom and occasional in-person sessions. These meetings are used to validate progress, receive feedback, and align academic expectations with the project timeline. Notes and decisions are documented in shared online documents.

Tool-Based Monitoring (Jira, GitHub, Mattermost)

Jira is used to manage the product backlog, user stories, and tasks. Each issue is linked to a use case or backlog item and contains an effort estimate and status (To Do / In Progress / Merge / In Review / UAT / Done). GitHub is used for version control, pull requests, and code reviews. Mattermost receives automatic notifications from both GitHub (commits, pull requests) and Jira (new/updated tasks), enabling real-time visibility of changes and progress.

Jira Comments and Cross-Task Communication

For each Jira task, the team actively uses the comment section to document additional information, clarifications, and decisions that are not fully captured in the task description. When a task has dependencies or important side effects on other tasks (for example, shared API changes or UI contracts), the related issues are linked in Jira and the responsible assignees are explicitly mentioned in the comments. In parallel, the team uses Mattermost mentions and channels to double check these critical points in real time (e.g., confirming an endpoint change with both backend and frontend owners). This approach ensures that stakeholders who might be affected by a change are notified early and that important decisions are not lost in private chats.

## Project Metrics

Project-level metrics focus on schedule alignment and remaining sprint workload. The team will collect a limited set of metrics that can be reliably obtained from existing tools without creating additional overhead.

Sprint Burndown and Remaining Work

What: Remaining work (story points / hours) compared to the sprint timeline.

How / When: Visualized in Jira during each sprint; updated whenever tasks move across workflow states.

Where Stored: Jira sprint boards and reports.

Why: To observe whether the sprint is progressing as expected and to identify potential spillovers early.

## Product Metrics

Product-level metrics are used to monitor whether the implemented system satisfies the requirements defined in the SRS and whether each increment is converging toward the expected scope.

Requirements and Use Case Coverage

What: Number and percentage of functional requirements and use cases that are fully implemented, partially implemented, or not implemented in the current increment.

How / When: After each increment, the team maps implemented features to SRS requirements and updates the coverage list.

Where Stored: A requirements coverage table in shared documents linked back to the SRS and prototype documentation.

Why: To verify that critical capabilities (authentication, map interaction, AI route generation, booking integration, etc.) are delivered in line with the planned scope.

Basic Performance Metrics (Prototype Level)

What: Observed response times for AI route generation, map loading, and booking result retrieval, compared against non-functional targets (e.g., route generation within around 10–15 seconds, map updates within a few seconds).

How / When: Measured informally during internal tests and demonstrations, recorded when problematic.

Where Stored: Test notes attached to Jira tasks and shared documents.

Why: To detect major performance issues early and plan optimization if key interactions become too slow.

## Process Metrics

Process metrics are used to evaluate whether the team is following its planned coordination and documentation practices consistently.

Meeting Adherence and Documentation

What: Percentage of planned daily/sprint meetings actually held, and percentage of those with documented notes.

How / When: Checked monthly based on calendar entries and meeting notes.

Where Stored: Shared documents (meeting minutes) and the team calendar.

Why: To ensure consistent communication, reduce misunderstandings, and maintain traceability of decisions.

Additionally, the team informally tracks the use of Jira comments and Mattermost mentions for cross-task dependency clarifications, as an indicator of communication quality.

## Data Storage and Usage of Metrics

All metrics are collected and stored using tools that are already part of the Vacanza project environment: Jira (task status and burndown), Mattermost (activity notifications and mentions), and shared online documents (meeting notes and requirement coverage tables). The collected metrics are primarily used to detect early if the team is behind schedule (e.g., sprint burndown indicating spillover risk), to support sprint replanning and task reassignment decisions, and to ensure that implemented functionality remains aligned with the SRS scope across increments.

# Software Development Environment

This section defines the Software Development Environment for the Vacanza project, i.e., the set of technologies and tools that will be used to develop, integrate, test, and deploy the system. The goal is to ensure a consistent baseline across team members, reduce environment-dependent issues, and support end-to-end traceability from requirements to tasks, code, and test evidence. The table below,  summarizes the selected stack for backend, web, mobile, and AI components, including programming languages and frameworks, database and external services/APIs, hosting, containerization and CI/CD, version control, project management, communication, and testing tools, together with the baseline version information where applicable. When exact versions are not fixed, the team will follow “latest stable” releases and record any changes in the project log to keep the baseline consistent.

Table 9 Software Development Environments

| Name | Type | Version | Description |
| --- | --- | --- | --- |
| Java | Programming Language | 17+ (compatible with Spring Boot 3.x) | Main backend implementation language used for the Spring Boot REST API server. |
| Python | Programming Language | 3.14 | Used in the AI microservice for route generation, persona modelling, and recommendation logic. |
| Dart | Programming Language | 3.x | Primary language for the Flutter-based cross-platform mobile client. |
| JavaScript (ES6+) | Programming Language | ES6+ | Used in the React web client and frontend build tooling. |
| Spring Boot | Backend Framework | 3.x | Core backend framework providing RESTful APIs, security, and integration with database and external services. |
| React.js | Frontend Framework | 18.x | Web UI framework used for the responsive Vacanza web client. |
| Flutter | Mobile UI Framework | 3.x | Cross-platform mobile framework used for Android/iOS Vacanza client. |
| FastAPI / Flask (Python) | Backend Framework / Microservice | Python 3.14 / FastAPI 0.121.0+ | Lightweight framework stack for the AI backend microservice exposing recommendation endpoints. |
| PostgreSQL | Relational Database | 18.x | Main relational database storing core application data (users, trips, itineraries, logs, etc.). |
| Firebase Authentication | Authentication Service | Latest stable | Provides secure user authentication (OAuth 2.0 / ID tokens) for Vacanza web and mobile clients. Firebase Realtime Database features are not used. |
| Mapbox API | Mapping API | Latest stable | Delivers interactive maps, POI visualization, and route rendering in web and mobile clients. |
| General Travel API | Third-Party Content API | Latest stable | Supplies travel-related data such as attractions, events, or city information consumed by the backend. |
| Calendar API | External Integration API | Latest stable | Used to synchronize Vacanza itineraries with external calendars (e.g., user’s personal calendar). |
| Docker | Containerization Platform | 28.x | Used to containerize backend, AI service, and database components for consistent deployment. |
| DigitalOcean Droplet | Cloud Hosting / IaaS | N/A (cloud service) | Cloud server environment hosting the containers (backend, database, AI service) and providing network and storage resources. |
| Git | Version Control System | 2.x | Distributed version control used locally by all team members for source code management. |
| GitHub | Remote Repository Hosting | Cloud (latest) | Central code hosting platform with pull requests, code reviews, and issue tracking linked to Jira. |
| GitHub Actions | CI/CD Service | Cloud (latest) | Automates build, test, and deployment workflows for backend and web components. |
| Jira | Project Management Tool | Cloud (latest) | Manages product backlog, sprints, user stories, tasks, and defect tracking for the project. |
| Mattermost | Team Communication Tool | Cloud / Self-hosted (latest) | Used for real-time communication, notifications from GitHub/Jira, and cross-task clarifications via mentions. |
| Google Docs | Documentation | Cloud (latest) | Used for collaborative documentation, metric tracking tables, test case definitions, and meeting notes. |
| Postman | API Testing Tool | Latest stable | Used to manually verify REST endpoints of the Spring Boot and AI backends during integration and system testing. |

During development, source code will be managed in Git/GitHub, tasks will be tracked in Jira, and day-to-day coordination will be handled via the team’s communication channel. Backend/AI services and the database will be run locally in a reproducible manner where possible (e.g., using Docker) to ensure consistent setups across developers. API verification will be supported through manual and automated testing tools (e.g., Postman and test frameworks listed in Table 9), and CI/CD pipelines will be used to automate build and test steps to detect issues early. Deployment and runtime hosting will follow the environment described in Table 9, ensuring that integration and release activities remain aligned with the defined baseline and provide auditable delivery evidence (commits, issues, test outputs, and documentation).

# Discussions

While preparing the SPMP document, our team encountered several practical challenges related to planning and coordination. One of the first questions was how to divide the sections in a fair and logical way: some parts (such as Agile Estimation, Cost Estimation, Resource Requirements) required deeper analysis and more calculations, whereas others were more descriptive. To avoid overloading certain members, we iteratively adjusted the section assignments and sometimes worked in pairs on the more complex parts. We also had to decide which sections should be reviewed collectively (for example, Agile Estimation, Work Breakdown Structure, and Risk-related content) to ensure that they were consistent with the especially SRS document. Another difficulty was deciding how detailed each part of the SPMP should be. For the WBS and work packages, we spent time discussing how far to break down tasks without losing readability, and for the cost and resource sections we had to choose a reasonable level of granularity (e.g., whether to include very small items such as individual beverages, or to group them under higher-level categories). Agile Estimation required particular attention: converting functional requirements into user stories, assigning story points, and connecting them with Use Case Points forced us to think carefully about relative complexity instead of guessing arbitrary numbers. Since there is rarely a single “correct” answer for these estimations or for scope-related decisions, we frequently consulted each other, compared different options, and aligned on a shared rationale rather than relying on one person’s judgment. Finally, time management under a heavy course load was an ongoing constraint. To keep control over the document quality, we set an internal target date earlier than the official deadline so that we could reserve time for a final joint review of all sections (formatting, terminology, cross-references). This process improved our understanding of project planning artifacts, clarified the relationships between effort estimation, cost, and resources, and strengthened our habit of making decisions collaboratively instead of working in isolation.

ChatGPT 5.2 Prompt: “Mevcut SPMP Executive Summary metnimi, aldığımız feedbacke göre revize et: tek paragraf, tam 1 sayfa, görselsiz; içine effort estimation sayıları ve toplam maliyeti mutlaka yaz (WBS ≈ 3,100 person-hours, UCP ≈ 3,080–3,100 person-hours, Agile ≈ 1,880 person-hours; total cost 19,920 TL + 360 USD), ‘man-hours’ yerine person-hours kullan, WBS’de documentation work packages olduğunu belirt ve SPMP’nin kapsadıklarını + bulgularımızı kısa ve net özetle.”

ChatGPT 5.2 Prompt: “Please write a concise, academic paragraph that summarizes this table. The paragraph should explain how the WBS was derived from the SRS (Functional Requirements and Use Cases), describe the logical execution flow starting from project management and documentation activities, and clarify the role of predecessor dependencies.”

Gemini Pro Prompt: “Create a detailed SPMP Work Packages table with granular IDs (X.X.X) for the Vacanza travel app according to our SRS document.”

ChatGPT 5 Prompt: “*all the explanations, figures and docs are given* can you explain wp’s and assigned members’ roles for 3 milestones”

ChatGPT 5 Prompt: “Here is the  requirement text for the subsection. We need to list all resources (personnel, hardware, software, facilities, travel, maintenance) as a function of time and link them to cost items. Please draft this section for the Vacanza project.”

ChatGPT 5 Prompt: “*listed probable costs* can you please help me estimate an average cost with the things that come to my mind”

ChatGPT 5 Prompt: “Here is the SPMP requirement text. We are students with no formal budget, but we still have costs like coffee in meetings, transportation, using our personal laptops, and AI subscriptions like ChatGPT. Please help me design this subsection according to this context. Also, using the calsulations, help me calculate and formulate them.”

ChatGPT 5 Prompt: “In the discussion part, explain how small recurring costs add up, how AI tools affect the budget, and how student discounts (Mapbox, DigitalOcean, vacanza.app domain) reduce our effective project cost.”

ChatGPT 5.2 Prompt: “Give us an introduction fort his section so that this table doesn't remain alone under this heading.”

ChatGPT 5.2 Prompt: “We currently have a Story Point table like this. However, when we created it, we didn't specify how we would define it or what we would do with it. Could you please provide me with a text file that fits this description?”

ChatGPT 5 Prompt: “Could you compare the results of the three different estimation methods used for the project WBS Decomposition-Based Estimation, Use Case Point (UCP) Estimation, and Agile Story Point Estimation?”

ChatGPT 5.2 Prompt: “Section 3 metnimi hocanın feedbackine göre sadeleştir: Velocity/WBS progress/milestone status/current status/issue cycle time/defect metrics/code review activity kısımlarını çıkar”

ChatGPT 5.2 Prompt: “can you write an introduction paragraph for the things that we’ve written”

ChatGPT 5 Prompt: “Create a concise table listing the software development environment (languages, frameworks, APIs, databases, cloud, project management, testing tools) with type, version, and short description for the Vacanza project.”

ChatGPT 5.2 Prompt: “can you write an explanation paragraph fort he table given, according to instructor’s feedback?”

ChatGPT 5 Prompt: “*all the difficulties are listed* can you please write them in academic english like the other documents’ discussions part?”